## Backlog
TaskID	Task	Estimation	Status	19	20	21	22	23	24	25	26	27	28
1	Define and estimate all tasks	2	Done	1
2	Document logic view / (include classes description)	2	Done										2
3	Document process view	2	Done										1
4	Document deployment view	2	Done										1
5	Document implementation view / (components diagram)	2	Done										1
6	Document use cases view / (include use case diagram)	2	Done			1							1
7	Investigate and select / Load testing utility / (document rationale)	4	Done										1
8	Document load testing	3	Done
9	Do AppEngine Python tutorial	4	Done	1	2		1
10	Implement use case: CreateEvent	4	Done						3
11	Implement use case: / ConfirmAttendance	4	Done						2	6
12	Implement use case: / CancelAttendance	4	Done								1	1	1
13	Implement use case: / CheckConfirmationStatus	4	Done								1	1	1
14	Create web interface	4	Done				1	1	1		1	1	1
15	Perform load testing	3	Done										1
16	Investigate GAE storage	2	Done						2
17	Learn Jinja2 basics	2	Done					1
18	Define system objectives	1	Done			1
19	Deploy app on the cloud	2	Done										1