## Backlog
TaskID	Task	Estimation	Status	19 – Mo	20 – Tu	21 – We	22 – Th	23 – Fr	24 – Sa	25 – Su	26 – Mo
1	Define and estimate all tasks	2	Done	1
2	Document logic view / (include classes description)	2	Pending
3	Document process view	2	Pending
4	Document deployment view	2	Pending
5	Document implementation view	2	Pending
6	Document use cases view / (include use case diagram)	2	Done			1
7	Investigate and select / Load testing utility / (document rationale)	4	Pending
8	Document load testing	3	Pending
9	Do AppEngine Python tutorial	4	In Progress	1	2		1
10	Implement use case: CreateEvent	4	Pending						2
11	Implement use case: ConfirmAttendance	4	Pending						2
12	Implement use case: CancelAttendance	4	Pending
13	Implement use case: CheckConfirmationStatus	4	Pending
14	Create web interface	4	In Progress				1	1
15	Perform load testing	3	Pending
16	Investigate GAE storage	2	Pending
17	Learn Jinja2 basics	2	Done					1
18	Define system objectives	1	Done			1
19	Deploy app on the cloud	2	Pending